## Sheet1
Id	Project	Reporter	Assigned To	Priority	Severity	Reproducibility	Product Version	Projection	Category	Date Submitted	ETA	OS	OS Version	Platform	View Status	Updated	Summary	Status	Resolution	Fixed in Version	Duplicate ID
106	ROACH V1.0	francois	francois	normal	feature	always		none		08/05/28	none				public	08/06/03	Request for POR on Actel	resolved	fixed		0
15	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/07	none				public	08/06/03	Add extra chip select from PPC to FPGA	resolved	fixed		0
107	ROACH V1.0	francois	francois	normal	tweak	always		none		08/05/30	none				public	08/06/03	Request for PERCLK to move to global clock net pin	resolved	fixed		0
109	ROACH V1.0	francois	francois	high	minor	always		none		08/06/03	none				public	08/06/03	DDR DIMM SDA and SCLK not connected to I2C bus	resolved	fixed		0
105	ROACH V1.0	francois	francois	normal	minor	always		none		08/05/28	none				public	08/05/30	Connectors populated with revere polarity SMA's	resolved	fixed		0
14	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/30	Add fiducials at all BGA packages (including U17, U63) and for PCB	resolved	fixed		0
25	ROACH V1.0	francois	francois	high	minor	sometimes		none		08/05/20	none				public	08/05/30	U6 and U7 misbehaving	resolved	fixed		0
108	ROACH V1.0	francois	francois	normal	tweak	always		none		08/05/30	none				public	08/05/30	Config Mode pins have possibility to cause clash on CPLD output pins	resolved	fixed		0
13	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/07	none				public	08/05/28	Tracks too close to mounting holes	resolved	fixed		0
1	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/06	none				public	08/05/28	LED's CR1 - CR10: Incorrect package fitted to board	resolved	fixed		0
2	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/06	none				public	08/05/28	LED's CR1-10 are fitted the wrong way round.	resolved	fixed		0
23	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/08	none				public	08/05/28	DDR2 socket clips (J15) fouls on ZDOK connector (P7), J15 must be moved.	resolved	fixed		0
24	ROACH V1.0	francois	francois	immediate	block	have not tried		none		08/05/12	none				public	08/05/28	10GbE Rx lines shorted	resolved	fixed		0
16	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/07	none				public	08/05/09	Clean up IIC - can remove U38, U39, U47	resolved	fixed		0
12	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/07	none				public	08/05/09	J24 and J22 mirrored	resolved	fixed		0
11	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/08	BGA vias are not covered	acknowledged	open		0
10	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/08	Pullup resistor needed on Virtex-5 done pin	resolved	fixed		0
7	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/07	none				public	08/05/08	Following 0402 caps are fitted to 0805 pads	resolved	fixed		0
6	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/07	none				public	08/05/08	R292 & R296 footprint is too small	resolved	no change required		0
9	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/08	R88 & R89 missing	resolved	no change required		0
5	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/08	R41 missing	resolved	no change required		0
4	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/06	none				public	08/05/08	U45-48 incorrect footprints	resolved	fixed		0
3	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/06	none				public	08/05/08	U31 - Incorrect footprint	resolved	fixed		0
17	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/08	Add orientation marks for U55-U59 - enable top-outlines in gerber generation	resolved	fixed		0
18	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/07	none				public	08/05/08	Correct ZDOK footprint	resolved	fixed		0
19	ROACH V1.0	alec	francois	normal	major	have not tried		none		08/05/07	none				public	08/05/08	Correct U50 footprint (hole size)	resolved	fixed		0
20	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/08	Correct J32 pin 1 indicator off board	resolved	fixed		0
21	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/08	Correct U25 part number - should be ADR03ARZ	resolved	fixed		0
22	ROACH V1.0	alec	francois	normal	minor	have not tried		none		08/05/07	none				public	08/05/08	Check SMAs - J10 and J11 for mounting - 90 degree possible depending on mated connector height	resolved	no change required		0